# Further Implementation of the Industrial Emissions Directive in Serbia

Terms of Reference

Local LTE – IPPC farms Expert

Project is funded by the Embassy of Sweden Belgrade

Project is implemented by the Cleaner Production Centre of the Faculty of Technology and Metallurgy University of Belgrade

# Position: Local Long Term Expert – IPPC farms Expert (ref. LLTE/FARMS)

# O

# Description of the project

# General objective of the project “Further Implementation of the IE Directive in Serbia” is to support the Serbian Competent Authorities and operators in the implementation of the IE Directive by carrying out a comprehensive analysis of the measures that operators have to implement in order to achieve full compliance with IED requirements. A special focus will be given to minimize the impact on environment of the Food production chain operators through specific consideration to measures related to energy and resources utilization. Additionally, the project will aim to foster technological improvement of operators in order to help them to comply their operation with best available techniques.

# This will be achieved through 4 main components of the Project and different activities that will involve all relevant stakeholders:

# Support in the preparation of the Directive Specific Implementation Plan (DSIP) for IED and environmental legislation related to IED implementation

# Technical support – direct support to the competent authorities and operators from the food production chain in the process of issuing integrated permits by preparing manuals, applications and relevant plans and draft permits; creation of network and help desk for operators

# Promotion of technological improvement - to foster the cooperation between Companies and University in order to promote environmental programs as well as to adopt innovative EU standards and develop new market opportunities; preparation of technology transfer projects

# Awareness and capacity building – organization of visibility events and various working groups.

# Description of the Local Long Term Expert activity

# The aim of the task is to support the project team in carrying out the activities of the project related to IPPC farms.

# In particular, the LLTE will be responsible of:

# Activity 2.4 Follow-up on IPPC farms project impact

# The activity is aimed to pursue the activities carried out during the previous project (IPPC farms) in supporting operators and CA in the integrated permitting process. In particular, the Expert will support Competent Authorities in the preparation of new integrated permits by utilizing the template developed during the previous project and organizing periodic meetings aimed to discuss common topics and issues related to permits preparation. The Expert will support also the operators keeping constant communication with them and operating a permanent help-desk that will be available for clarifications, information and support at technical and administrative level.

# Activity 1.2 Technical and financial assessment of the compliance of IPPC farms to IED requirements

# The LLT Expert will support international and local experts engaged in this activity by collecting and providing necessary information on IPPC farms, needed for the technical and financial analysis and the revision of the IED DSIP. In particular, support will include the preparation of the information required by the experts, contact with operators, competent authorities etc.

In order to complete the task in the most effective way, the selected Expert will work at the project office and in strict cooperation with the Department for Integrated Permits of the Ministry of Environmental Protection and with local authorities; the Expert will be also required to visit independently the selected IPPC farms and to organize, in cooperation with the project team, workshops and meetings involving farms and competent authorities.

# Job description:

Specific tasks of the selected Expert will be:

    - Activity 1.2:

  - Support to technical and financial experts in the collection of data on IPPC farms;

  - Check of the final draft of the IED DSIP and its part and documents related to IPPC farms

    - Activity 2.4:

- Preparation of 10 draft integrated permits for farms: the Expert will support the project team in selecting, in agreement with MEP, 10 IPPC farms which will be supported in the process of obtaining the integrated permit. The support will include: identification of the criteria for the selection, preparation of the final selection list and contact with the selected farms. The Expert will, then, utilize the template developed by the previous project for the preparation of the integrated permits for selected farms. Following the methodology developed during the previous project and in cooperation with the Competent Authorities and other experts, the LLT Expert will carry out BAT assessment, check of the Plan of measures, draft of the integrated permit and check of the documents to be attached to the permit. The task is aimed to support, at the end, the Competent Authorities in the process of issuance of the integrated permit.

- Creation of the IPPC farms network: the Expert, in cooperation with the project team, will organize periodic meetings, e.g. every 3 months, with the Competent Authorities and Inspectors involved in integrated permitting for farms, continuing the activity established during the project IPPC farms. The meetings could also include the Competent Authorities for manure management in order to discuss the issues related to this topic and specific conditions for lagoons. This network will be established with the purpose of providing the involved Institutions with the opportunity to discuss common topics and problems while sharing different solutions and harmonizing their approach. The Expert will be responsible for the preparation of these meetings in order to follow up on the status of applications and draft permits prepared within the previous Project and give additional support, if needed, in order to finalize the process of issuance the permits. By the end of the project, the Expert is asked to support MEP in the creation of a permanent network of IPPC Farms and Competent Authorities.

- IPPC farms Help Desk: the Expert will be responsible, in cooperation with the project team, for the creation of a Help-Desk for farms and CAs. The Expert will be available during the whole duration of the project, at the project office and via email for questions and support on IPPC documents’ preparation. Within this task, the Expert will be asked to provide direct support or discuss the requested clarifications with MEP or other Institutions; the aim of this task is to support operators and CAs in a harmonized implementation of IPPC in Serbian farms.

# Period of the Assignment:  April 2018 – August 2020

# Number man/days allocated: full-time during the period of the assignment

# Location of the assignment: Belgrade, Serbia and on-site at the assigned installations

# Qualification and skills

| Education | University degree in Technical Sciences, Agriculture, Environmental Management or equivalent subject. A PhD in a subject relevant to the assignment is an advantage |
| --- | --- |
|  | At least very good command of English (4 on a scale 1-5 where 5 is excellent) |
| Professional Experience | - At least 10 years of post graduate professional experience in environmental management - At least 5 and preferably 6 years of post graduate professional experience in environmental and technical analysis of IPPC installations - Experience with environmental analysis of IPPC farms - Proven knowledge of national environmental legislation and EU legislation in the area of IPPC/IE and Nitrate Directive - Work experience in projects in the fields related/similar to the contract is considered as an advantage |
| Other | - Valid driving licence |